## BURNDOWN CHARTS
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0 to 10) | Priority | Risk | Assign | Sprint
OPTION 1: CARPOOLING / CAR SHARING SYSTEM
#10 (US-10) | Task 10.1. User can select option to enable carpooling/car sharing | - add user model boolean property "carpool" - add carpooling tab | 3 | MED | LOW | Khaled | 4
#10 (US-10) | Task 10.2 User can specify rental preferences | - ability to select rental range - ability to select rental budget - ability to filter based on branch location, year, type.... | 4 | HIGH | LOW | Safaa | 4
#11 (US-11) | Task 11.1 User can describe self and see other users' descriptions | - only display users with carpool enabled - ability to write description | 7 | HIGH | MED | Jadon | 4
#11 (US-11) | Task 11.2 Users can contact each other with provided contact information | - display email and contact info only if both users approve | 7 | LOW | MED | Jadon | 4
#11 (US-11) | Task 11.3 Users can confirm carpooling arrangement | - all users send a confirmation - reception of all confirmations by admin is necessary for creating reservation | 9 | HIGH | MED | Matia | 4
#12 (US-12) | Task 12.1 Users can make a reservation via Admin | - only admin can create the reservation - admin can check in & check out | 4 | HIGH | LOW | Khaled | 4
#12 (US-12) | Task 12.2 Users get reservation confirmation | - display price for each user - display usual reservation details | 7 | MED | LOW | Jadon | 4
OPTION 2: GET BEST PRICING OPTIONS DEPENDING ON RENTAL PERIOD
#10 (US-10) | Task 10.1. User can view high demand periods and prices associated to certain dates | - implement different prices for different high demand periods (ex. holidays, weekends) | 8 | HIGH | LOW | Safaa | 4
#10 (US-10) | Task 10.2. User can sort car models by price | - filter by price high to low, vice-versa
#10 (US-10) | Task 10.3. User can specify prefered range | - option to specify range - option to specify number of days of rental - display min and max price | 5 | MED | LOW | Matia | 4
#10 (US-10) | Task 10.4. User can switch car type/model to see different pricing options | - implement a car model switching option | 8 | HIGH | HIGH | Khaled | 4
#9 (US-9) | Task 9.2. User gets confirmation whether check-out was successful | - display confirmation message if branch exists - verify check-out data (validate form) (backend) | 8 | MED | HIGH | Safaa | 4
#9 (US-9) | Task 9.2. User views reservation summary | - display car database details - display branch contact info and details - display reservation details | 4 | MED | LOW | Jadon | 4
#9 (US-9) | Task 9.2. User can review and confirm details at check-out | - display list of cars - display list of specifications for each car | 4 | MED | LOW | Matia | 4
#9 (US-9) | Task 9.3. User can pay online at check-out | - create payment form (frontend) | 3 | HIGH | LOW | Khaled | 4
#9 (US-9) | Task 9.3. User can pay online at check-out | - encrypt and secure user payment data (backend) | 7 | MED | MED | Safaa | 4