## Sheet1
Team Members
[6 empty] | First Name | Last Name | Student ID | Nickname
[6 empty] | Jadon | Games | 40173613 | jadon
[6 empty] | Matia | Komsic | 40175388 | matia
[6 empty] | Khaled | Rezgui | 40176606 | khaled
[6 empty] | Safaa | Kentaoui | 40228872 | safaa
Log Table
Date | Who |  |  |  | Activity | Hours Spent | Detail | Result | Hours Spent |  |  |  | total
| jadon | matia | khaled | safaa |  |  |  |  | jadon | matia | khaled | safaa
Sprint 3
2024-03-18 | 1 | 1 | 1 | 1 | Meeting | 0.5 | Discussion on plans for Sprint 3 | Discussion and distribution of tasks | 0.5 | 0.5 | 0.5 | 0.5
2024-03-22 | 1 | 1 | 1 | 1 | Meeting | 2 | Meeting during Lab | Demo of Sprint 2 core features, dicussion for next sprint | 2 | 2 | 2 | 2
2024-03-24 | 0 | 0 | 1 | 0 | Meeting | 8 | Start of Process 1 | Task completed | 0 | 0 | 8 | 0
2024-03-25 | 1 | 1 | 1 | 1 | Meeting | 0.5 | Discussion of core features and acceptance tests | Completion of process 1 and near-completion of process 2 | 0.5 | 0.5 | 0.5 | 0.5
2024-03-25 | 1 | 0 | 0 | 0 | Task | 5 | Fixing the Unit Tests for each code file | Task completed | 5 | 0 | 0 | 0
2024-03-25 | 0 | 0 | 0 | 1 | Task | 5 | Creating Database variable for the acceptance form | Task completed | 0 | 0 | 0 | 5
2024-03-25 | 0 | 0 | 1 | 0 | Task | 10 | Start of Process 2 | Task completed | 0 | 0 | 10 | 0
2024-03-26 | 1 | 1 | 1 | 1 | Meeting | 0.5 | Progress check for core features and tasks | Completion of process 2 and start/work on process 3 | 0.5 | 0.5 | 0.5 | 0.5
2024-03-26 | 0 | 0 | 1 | 0 | task | 10 | Last minute work for the sprint deadline | Process 3 completed | 0 | 0 | 10 | 0
2024-03-26 | 0 | 1 | 0 | 0 | task | 5 | Completing the Diagrams | Task completed | 0 | 5 | 0 | 0
2024-03-26 | 1 | 0 | 0 | 0 | task | 8 | Integration of continous pipeline and documentation | Completing inegration and documention | 8 | 0 | 0 | 0
2024-03-26 | 0 | 0 |  | 1 | task | 6 | Last minute work for the sprint deadline | Additional documentation | 0 | 0 | 0 | 6
[8 empty] | Total hours | 16.5 | 8.5 | 31.5 | 14.5
[8 empty] | Total team hours |  |  |  |  | 71