## BURNDOWN CHARTS
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0 to 10) | Priority | Risk | Assign | Sprint
#7 (US-7) | Task 7.1. User can search branch by location | - display all branches around specified location (frontend) | 3 | HIGH | LOW | Khaled | 3
#7 (US-7) | Task 7.2 User can view branch details | - display branch location - display branch operating hours - display branch cars - display branch contact details (frontend) | 4 | HIGH | LOW | Safaa | 3
#7 (US-7) | Task 7.1. User can search branch by location | - implement branch search functionality (backend) | 7 | HIGH | MED | Jadon | 3
#7 (US-7) | Task 7.3. Admin can delete branch | - implement backend functionality to CRUD branch | 7 | LOW | MED | Jadon | 3
#7 (US-7) | Task 7.2 User can view branch details | - implement backend functionality to view branch for users | 9 | HIGH | MED | Matia | 3
#8 (US-8) | Task 8.1. User can check in branch | - create form to check in branch (frontend) | 4 | HIGH | LOW | Khaled | 3
#8 (US-8) | Task 8.2. User gets confirmation whether check-in was successful | - display confirmation message if branch exists - verify check-in data (validate form) (backend) | 7 | MED | LOW | Jadon | 3
#8 (US-8) | Task 8.2. User views available cars at branch | - display all cars available at branch (frontend) |  | HIGH | LOW | Safaa | 3
#8 (US-8) | Task 8.2. User views available cars at branch | - connect all cars available at branch to car info (backend) | 5 | MED | LOW | Matia | 3
#9 (US-9) | Task 9.1. User can check out branch | - create form to check out branch (frontend | 4 | HIGH | HIGH | Khaled | 3
#9 (US-9) | Task 9.2. User gets confirmation whether check-out was successful | - display confirmation message if branch exists - verify check-out data (validate form) (backend) | 8 | MED | HIGH | Safaa | 3
#9 (US-9) | Task 9.2. User views reservation summary | - display car database details - display branch contact info and details - display reservation details | 4 | MED | LOW | Jadon | 3
#9 (US-9) | Task 9.2. User can review and confirm details at check-out | - display list of cars - display list of specifications for each car | 4 | MED | LOW | Matia | 3
#9 (US-9) | Task 9.3. User can pay online at check-out | - create payment form (frontend) | 3 | HIGH | LOW | Khaled | 3
#9 (US-9) | Task 9.3. User can pay online at check-out | - encrypt and secure user payment data (backend) | 7 | MED | MED | Safaa | 3