## Sheet1
Team Members
[6 empty] | First Name | Last Name | Student ID | Nickname
[6 empty] | Jadon | Games | 40173613 | jadon
[6 empty] | Matia | Komsic | 40175388 | matia
[6 empty] | Khaled | Rezgui | 40176606 | khaled
[6 empty] | Safaa | Kentaoui | 40228872 | safaa
Log Table
Date | Who |  |  |  | Activity | Hours Spent | Detail | Result | Hours Spent |  |  |  | total
| jadon | matia | khaled | safaa |  |  |  |  | jadon | matia | khaled | safaa
Sprint 4
2024-04-01 | 1 | 1 | 1 | 1 | Meeting | 2 | Online discord meeting on sprint 4 brief | established what was the feature we should implement for the following sprint (sprint 4) | 2 | 2 | 2 | 2
2024-04-02 | 0 | 0 | 1 | 0 | Development | 6 | Full stack development | Make the user able to add other users to the reservation and Make the other users able to access the shared reservation and confirm | 0 | 0 | 6 | 0
2024-03-08 | 0 | 1 | 0 | 0 | Documentation | 6 | Documenting Diagram | Documentation of Diagram per user story | 0 | 6 | 0 | 0
2024-04-03 | 0 | 0 | 0 | 1 | Development | 4 | Database | Database adaptation to new fucntions | 0 | 0 | 0 | 4
2024-04-05 | 1 | 0 | 0 | 0 | Development | 6 | Full stack development | Make the checkIn and checkout process shared between current reservation users | 6 | 0 | 0 | 0
2024-04-06 | 1 | 1 | 1 | 1 | Meeting | 1 | Team meeting | we updated eachother on the tasks we are on and the advancement of the implementation of the car sharing system | 1 | 1 | 1 | 1
2024-04-06 | 0 | 0 | 1 | 0 | Development | 6 | Full stack development | Split the price and ask for each shared user to pay their part. | 0 | 0 | 6 | 0
2024-04-06 | 0 | 0 | 0 | 1 | Development | 4 | Database | Additional work on database queries | 0 | 0 | 0 | 4
2024-04-06 | 1 | 1 | 1 | 1 | Meeting | 2.5 | Lab meeting | Features demo to the TA, feedback received | 2.5 | 2.5 | 2.5 | 2.5
2024-04-08 | 0 | 0 | 1 | 0 | Development | 6 | Full stack development | Send confirmation email to each added user | 0 | 0 | 6 | 0
2024-04-09 | 0 | 0 | 0 | 1 | Documentation | 4 | Powerpoint work | Work on Powerpoint slides | 0 | 0 | 0 | 4
2024-04-09 | 0 | 0 | 1 | 0 | Documentation | 4 | Powerpoint work | Work on Powerpoint slides | 0 | 0 | 4 | 0
2024-04-09 | 1 | 0 | 0 | 0 | Documentation | 4 | Powerpoint work | Work on Powerpoint slides | 4 | 0 | 0 | 0
2024-04-09 | 0 | 1 | 0 | 0 | Documentation | 2 | Powerpoint work | Work on Powerpoint slides | 0 | 2 | 0 | 0
2024-04-09 | 1 | 1 | 1 | 1 | Meeting | 2 | Team meeting | separated the tasks and how the presentation should go on, who will say what. | 2 | 2 | 2 | 2
2024-04-10 | 1 | 0 | 1 | 0 | Documentation | 1 | Documenting meeting minutes | Throughout the sessions, meeting minutes were logged in and displayed in the repos | 1 | 0 | 1 | 0
[8 empty] | Total hours | 18.5 | 15.5 | 30.5 | 19.5
[8 empty] | Total team hours |  |  |  |  | 84