## Sheet1
Team Members
[6 empty] | First Name | Last Name | Student ID | Nickname
[6 empty] | Jadon | Games | 40173613 | jadon
[6 empty] | Matia | Komsic | 40175388 | matia
[6 empty] | Khaled | Rezgui | 40176606 | khaled
[6 empty] | Safaa | Kentaoui | 40228872 | safaa
Log Table
Date | Who |  |  |  | Activity | Hours Spent | Detail | Result | Hours Spent |  |  |  | total
| jadon | matia | khaled | safaa |  |  |  |  | jadon | matia | khaled | safaa
Sprint 1
2024-02-16 | 1 | 0 | 1 | 1 | Meeting | 2 | Team meeting on sprint 2 brief | first meeting, introductions, and plans for meeting in person. Plan for the used framework | 2 | 0 | 2 | 2
2024-02-19 | 1 | 1 | 1 | 1 | Meeting | 0.5 | Sprint planning | Assigned rolls to all member and task were given | 0.5 | 0.5 | 0.5 | 0.5
2024-02-23 | 1 | 1 | 1 | 1 | Meeting | 0.5 | Srum meeting: What we did during the week/what we will do during spring break | Team has an idea of where we are in development | 0.5 | 0.5 | 0.5 | 0.5
2024-03-06 | 0 | 0 | 1 | 0 | Development | 5 | Front end application development | Search Functionality + Car browsing page works | 0 | 0 | 5 | 0
2024-03-06 | 0 | 0 | 0 | 1 | Development | 5 | Backend application development | Database + CRUD operations on users and cars are working | 0 | 0 | 0 | 5
2024-03-06 | 0 | 0 | 0 | 1 | Development | 3 | Backend application development | CRUD operations on reservations are working | 0 | 0 | 0 | 3
2024-03-08 | 0 | 0 | 0 | 1 | Documentation | 1 | Planning sprint 3 | Document for sprint 3 planning is done | 0 | 0 | 0 | 1
2024-03-08 | 1 | 1 | 1 | 1 | Meeting | 2.5 | Lab meeting | Features demo to the TA, feedback received | 2.5 | 2.5 | 2.5 | 2.5
2024-03-08 | 1 | 0 | 0 | 0 | Documentation | 1 | Documenting meeting minutes | Throughout the sessions, meeting minutes were logged in and displayed in the repos | 1 | 0 | 0 | 0
2024-03-10 | 0 | 0 | 1 | 0 | Development | 6 | Full stack development | Car/Reservation list are now displayed, linked to the backend/db | 0 | 0 | 6 | 0
2024-03-11 | 1 | 0 | 0 | 0 | Development | 6 | Unit tests/AT | Repos now has unit tests and acceptance tests for continuous integration | 6 | 0 | 0 | 0
2024-03-11 | 0 | 0 | 1 | 0 | Development | 5 | Full stack development | User can now login, we can keep track of which one is logged and make reservation based on logged user | 0 | 0 | 5 | 0
[8 empty] | Total hours | 12.5 | 3.5 | 21.5 | 14.5
[8 empty] | Total team hours |  |  |  |  | 52
Formulas:
Date = [Date, row above]
Date = [Date, row below]